## Summary PMO
📊 Overall Task Summary |  | 📄 Current View: | All
Metrics | Count | Label | Value
📋 Total Tasks | 110 | ✅ Completed | 76.36%
✅ Completed | 84 | 👀 Remaining | 23.64%
🔄 In Progress | 11
⏳ Not Started | 4
🚫 Blocked | 0
👀 Reviewing | 6
⚠️ Overdue | 18
⏸️ Temporary Hold | 2
📈 Overall Completion % | 76.36%
PMO Metrics Overview

## Bug Hunting Campaign
Category | Task | Status | Owner | Stage | Due date | Risk | Notes | Column 1
Bug Hunting Campaign 2025 | Email - 1.2 Re-engage Previous Year Participants | Completed | galina@cyberbay.tech tom@cyberbay.tech | Pre-event | 2025-06-17 |  | Copy - Tom and Galina - 12th Jun 2025 Template: https://www.notion.so/Email-2-1a-Re-engaging-previous-participants-Badge-Earned-Corp-1-20df6cda5915803d91f0fac30fd2ff2d?source=copy_link Dev team - 16th Jun 2025 (one off email) Reschedule 17th Jun to prepare template and mail list
Bug Hunting Campaign 2025 | Website - Landing Page | Completed | heidi fung | Pre-event | 2025-06-06 |  | Design - Zara - 4th Jun 2025 Coding - Dev team - 6th Jun 2025 Dev team: Including Upcoming event at Main homepage and BugHunting event landingpage
Bug Hunting Campaign 2025 | Marketing - Flyer | Completed | heidi fung | Pre-event | 2025-06-12 |  | Design from Freelancer
Bug Hunting Campaign 2025 | Website - QR Code to go to Landing Page | Completed | heidi fung | Pre-event | 2025-06-06 |  | Coding - Dev team - 6th Jun 2025 URL for Landing page will be https://cyberbay.tech/events/protectHK2025
Bug Hunting Campaign 2025 | Workflow - Sponsor to Sign in for Referee | Not started | heidi fung | Pre-event | 2025-06-26 |  | Heidi - get the list form sponsors - 20th Jun 2025 (The sponsor not yet give us the referees list - Recent update - 1st July 2025) Coding - Dev team - 26th Jun 2025 1. Sponsors will proivde a list of Referee emails (~ 200 emails account) 2. Creates account for the Referee - Label or Tag to corresponding Sponsors 3. Sponsors and Cyberbay should be able to login Corporates acccount for administration - SponsorSupport+CorpABC@sponsor.com - BugHunting+CorpABC@cyberbay.tech Check with Heidi
Bug Hunting Campaign 2025 | Website - Sign-Up form , Corporates and BH | Completed | heidi fung | Pre-event | 2025-06-06 |  | Design - Zara - 12th Jun 2025 Coding - Dev team - 16th Jun 2025 1. Embedded Promo code "protecthk2025" 2. to deffraintate the corporates for BugHunting2025 and other exsisting customers 2.1 seperate email flows for BugHunting related updates 2.2 dash board after login should be different, Completetion Rate for badge earning should be shown for BugHunting participants, but not the exsisting customers
Bug Hunting Campaign 2025 | Email - 1.1 Welcome & Enrollment Emails | Completed | heidi fung | Pre-event | 2025-06-09 |  | Copy - Natalie - 6th Jun 2025 Coding - Dev team - 9th Jun 2025
Bug Hunting Campaign 2025 | Email -1.3 Nudge HK BH for upcoming BugBounty Event | Completed | heidi fung | Pre-event | 2025-06-23 |  | Trigger: one off Copy - Natalie - 17 Jun Vetted Hunter list - Heidi 20 Jun Dev team - 23h Jun 2025 (one off email)
Bug Hunting Campaign 2025 | Website - Sign-Up form , Generate Referral Code for each Sponsors | Completed | heidi fung | Pre-event | 2025-06-20 |  | Coding - Dev team - 20th Jun 2025 -Generate specific Referral Code for each sponsors -Use for the list of referees from sponsors System generate automatically
Bug Hunting Campaign 2025 | Website - Corp - Sign UP - OTP quang@cyberbay.tech Any update requried or we can use current flow? | Completed | heidi fung | Pre-event | 2025-06-12 |  | Design - Zara - 9th Jun 2025 Coding - Dev team - 12th Jun 2025
Bug Hunting Campaign 2025 | Website - Corp/BH - Sign In quang@cyberbay.tech Any update requried or we can use current flow? | Completed | heidi fung | Pre-event | 2025-06-12 |  | Design - Zara - 9th Jun 2025 Coding - Dev team - 12th Jun 2025
Bug Hunting Campaign 2025 | Website - Corp/BH - Sign In- OTP quang@cyberbay.tech Any update requried or we can use current flow? | Completed | heidi fung | Pre-event | 2025-06-12 |  | Design - Zara - 9th Jun 2025 Coding - Dev team - 12th Jun 2025
Bug Hunting Campaign 2025 | Website - Corp - Bountystreak | Completed | heidi fung | During event | 2025-06-18 |  | Design - Zara - 9th Jun 2025 Coding - Dev team - 11th Jun 2025 The page showing - Listed Bounty mission - Badge completion rate Design - update wordings from 2024 Note 12 Jun: Deployed to PRD Pending: Update new design ( add 2 tooltips) and fix the redirection after signing in successfully Note 13 Jun: - Add card to the Bounty Mission page - Update counter logic Note 18 Jun: Update issue
Bug Hunting Campaign 2025 | Logic -Bounty Rewards setting | Completed | heidi fung | During event | 2025-06-18 |  | Coding - Dev team - 18th Jun 2025 Bounty set by Cyberbay but not participants: Cap amount critical bug Critical 7,000 High: 5,000, Med/Low 1000 Utilisation: Tier 1: Default Value: 7000 ¦ 5000 ¦ 1000 , Cumulative Total>= 5000 to Tier 2 Tier 2: Default Value: 4200 ¦ 3000 ¦ 600 , Cumulative Total>= 8000 to Tier 3 Tier 3: Default Value: 2520 ¦ 800 ¦ 0
Bug Hunting Campaign 2025 | Logic -Bounty Rewards setting - No bugs found | Completed | heidi fung | During event | 2025-06-18 |  | Coding - Dev team - 18th Jun 2025 Schedule every 3 days Check list of corporates with NO bug findings. Increcase the amount as follow Original: 100% (7000,5000,1000) after 3 days: 8000 ¦ 6000 ¦ 2000 after 6 days 9000 ¦ 7000 ¦ 3000 after 9 days 10000 ¦ 8000 ¦ 4000 (Add $1000 for every 3 days)
Bug Hunting Campaign 2025 | Website - Corp - Reports | Completed | heidi fung | During event | 2025-06-18 |  | Coding - Dev team - 18th Jun 2025 Crop - Reports Pages 1. Default Page 2. Reports auto purchase within first month of Campaign (like premium) 3. Pending Re-test 4. Retest un-resolved 5. Selected Checked Box New Logic 1st month (July) - the corporates would be treated as premium clients 2nd month (Aug) -new reported bugs needed to be purchased Remarks : in August corporates should be still able to access to bug reports found in July
Bug Hunting Campaign 2025 | Veeting BH | Completed | heidi fung | Pre-event | 2025-06-20 |  | HKPF - Louis confirmed the vetted list will be ready by 20 June
Bug Hunting Campaign 2025 | Marketing - Flyer | Completed | heidi fung | During event |  |  | Content - Heidi and Galina 13th Jun 2025 Coding - Dev team - 18th Jun 2025 Reminder to launch mission and verify assets for corporate 3 days after first registration
Bug Hunting Campaign 2025 | Website - Link/Button/ Pop-up/Carousell to show BugHunting 2025 and to the landing page | Completed | heidi fung | Pre-event | 2025-06-12 |  | Design - Zara - 9th Jun 2025 Coding - Dev team - 12th Jun 2025
Bug Hunting Campaign 2025 | Website - Corp - List Bounty | Completed | heidi fung | During event | 2025-06-18 |  | Coding - Dev team - 18th Jun 2025 Launch Bounty Program 1. Bounty details 2. Set up Targets 3. Rewards Setting (Default Value [refer to reward setting], Locked and cannot update by Crops) 4. Review Terms 5. Verify Assets (If refered by sponsor i.e. with referral code, no need to verify Assests) 6. Credentials
Bug Hunting Campaign 2025 | Dev- Create Cyberbay Support account for Self-registration Company | Completed | quang@cyberbay.tech | Pre-event | 2025-07-01 |  | for every self-registration, please batch create account like the following example e.g. bughunting+CoEmailDomain@cyberbay.tech pwd: ¦3H+CoEmailDomain so that we will have account that can help manage the missions for the participants.
Bug Hunting Campaign 2025 | Dev-Set up mission for Self-Registration/ Opt-in Previous participants | Completed | quang@cyberbay.tech | Pre-event | 2025-07-02 |  | Keep update before the start of mission
Bug Hunting Campaign 2025 | CyberScan for newly Registration | In progress - Dev | quang@cyberbay.tech | Pre-event | 2025-07-05 |  | Run Daily, tracker sheet "Self-Registration" 1. update column H for domain confirmation 2. after Domain confirmation run the full cyberscan
Bug Hunting Campaign 2025 | BH Page, Remove Filter "BugHunting 2024" | Completed | quang@cyberbay.tech | Pre-event | 2025-06-20 |  | Coding - Dev team - 20th Jun 2025
Bug Hunting Campaign 2025 | Bh Page, Add Filter "BugHunting 2025" | Completed | quang@cyberbay.tech | Pre-event | 2025-06-23 |  | Only show to the vetted hunter list - 23 Jun 2025 filter the BugHunting related missions to the Vetted hunters, the filter should be removed after 31 Aug 2025 Update: Release the missions at 00:00 on July 2 HKT
Bug Hunting Campaign 2025 | Referral Code - Oh360 | Completed | quang@cyberbay.tech | Pre-event | 2025-06-24 |  | Dev Team Due date: 24 June Create 1 URL and 2 QRcode for signup with: (auto-filled) Promo code: protecthk2025 (auto-filled) Referral code: Oh360 https://www.notion.so/protecthk2025-referral-Oh360-218f6cda591580c5b748d790fe60c3e4
Bug Hunting Campaign 2025 | Only Vetted BH can see the protecthk2025 missions | Completed | quang@cyberbay.tech | During event | 2025-07-02 |  | Update: Release the missions at 00:00 on July 2 HKT Finished logic at STG env
Bug Hunting Campaign 2025 | ProtectHK2025 dashboard. | Completed | tan@cyberbay.tech | During event | 2025-07-11 |  | Tan- Tracker sheet "2025 Dashboard" Pending artifact report data. Once this data is available in Production, it will take 3–4 days to complete the task
Bug Hunting Campaign 2025 | Dev Team investigation - Previous registration users cannot view the BH card in missions page Corporate user (without pomo code ) can view the Streak page from the Account Setting tab | Completed | Thuy (Sweet) Phan Thanh | Pre-event | 2025-06-18
Bug Hunting Campaign 2025 | Convert Previous participants with no reply Corp to be 2025 participants and ONLY do the Cyberscan wihtout active missions | Completed | Thuy (Sweet) Phan Thanh | Pre-event | 2025-06-24 |  | Tracking till 24 Jun
Bug Hunting Campaign 2025 | Upsell 2.1 - Define event triggers: Time-based Triggers | Completed | Tom Austin | During event | 2025-06-20 |  | See here in notion
Bug Hunting Campaign 2025 | Upsell 2.2 - Define event triggers: Additional Triggers | Completed | Tom Austin | During event | 2025-06-20 |  | See here in notion
Bug Hunting Campaign 2025 | Send mail for previous participants - Who didnt reply us til 24 Jun | Completed | Thuy (Sweet) Phan Thanh | Pre-event | 2025-06-26 |  | Heidi is preparing the content
Bug Hunting Campaign 2025 | Upsell 3 - Build user cohort based on behaviour (Cyberscan results, industry) | Completed | Tom Austin | During event | 2025-06-30 |  | This will be manual as building this into the system will take some time. Blocked: We need to wait for (1) more participating orgs to register and (2) cyberscans to be run for these participating orgs
Bug Hunting Campaign 2025 | Upsell 6 - Design visual elements | Completed | Tom Austin | During event | 2025-06-20 |  | The design of billboard banners [in progress by Zara] + splash page [not started, awaiting copy review by Galina]
Bug Hunting Campaign 2025 | Upsell 8 - Set up delivery rules and logic (following on from task Upsell 5) | Completed | Tom Austin | During event | 2025-06-30 |  | This will be manual as building this into the system will take some time. Blocked: We need to wait for (1) more participating orgs to register and (2) cyberscans to be run for these participating orgs
Bug Hunting Campaign 2025 | Upsell 9 - Upsell landing/splash page on website | Reviewing | Tom Austin | During event | 2025-06-23 |  | Upsell splash page copy as follows; awaiting copy review from Galina Kho then design will create the page - see here for copy
Bug Hunting Campaign 2025 | Upsell 7 - Select notification type | Completed | Tom Austin | During event | 2025-06-25 |  | Billboard bannner, once click the CTA will open a splash page with more info on the discount + link to upgrade request page (this will need to built into the website by devs)
Bug Hunting Campaign 2025 | Upsell 1 - Decide upsell products and features | Completed | Tom Austin | During event | 2025-06-25 |  | As follows; 1yr Cyberscan, 1yr Bug bounty, Consultation Review. Please see here
Bug Hunting Campaign 2025 | Upsell 4 - Set thresholds for triggers/notifications | Completed | Tom Austin | During event | 2025-06-25 |  | I've documented the triggers and their thresholds - although at present this will be manual task owned by me (Tom Austin) - please see here
Bug Hunting Campaign 2025 | Upsell 5 - Upsell copy for Time-based triggers for in-platform billboard + sidebar banners | Completed | Tom Austin | During event | 2025-06-20 |  | Please see here for in-platform banner copy, please review Galina Kho
Bug Hunting Campaign 2025 | Upselling Design Implementation | Completed | zara.amirzade@cyberbay.tech | During event | 2025-06-24 |  | Blocker: Waiting on finalized sales plan/copy from Tom (Sales Lead)
Bug Hunting Campaign 2025 | Upsell 10 - Write copy for each additional trigger | Completed | Tom Austin | During event | 2025-06-25
Bug Hunting Campaign 2025 | Upsell 2.2.1 - Event trigger tweaks | Completed | Tom Austin | During event | 2025-06-25
Bug Hunting Campaign 2025 | Upsell 11 - Review Modal Copy for both event triggers (2.1) and additional triggers (2.2) | Completed | Tom Austin |  |  |  | Please Review the copy
Bug Hunting Campaign 2025 | New BH for HKPF's Vetting | Completed | quang@cyberbay.tech | Pre-event | 2025-06-27 |  | list of bounty Hunters ( Hong Kong ), already passed KYC from 20 May 2025 - 27 June 2025,
Bug Hunting Campaign 2025 | Merge Supporting account with participant's account | Completed | quang@cyberbay.tech | Pre-event | 2025-07-01 |  | On-going For the corporates that Andy already created support account. https://docs.google.com/spreadsheets/d/1g_l0jNk4FNBBlz-bGOmLocqVXfsMjyY3OnXdsq0_EIg/edit?gid=434141066#gid=434141066 Please merge the accounts (the corporate ID of supporting account and client signup should be the same) e,g, BEHL is having 2 corporate id 034d9bb5-a730-4c1e-82f3-590e175a76c8 ff9a69a1-e388-422b-8887-8bcaf708ca9d
Bug Hunting Campaign 2025 | Enrol Previous participant to event code "protecthk2025" | Completed | quang@cyberbay.tech | Pre-event | 2025-06-30 |  | please check of the list of participants had put on "protecthk2025" event code list. https://docs.google.com/spreadsheets/d/1g_l0jNk4FNBBlz-bGOmLocqVXfsMjyY3OnXdsq0_EIg/edit?gid=434141066#gid=434141066 a98743e9-1cb7-4e4b-8503-c00eb081d740 VANKE HOLDINGS (HONG KONG) COMPANY LIMITED contacted and mentioned that they can only see 2024 records but not for 2025. please advise after the update is done and i will get back to the client.
Bug Hunting Campaign 2025 | Enrol Previous participant to event code "protecthk2025" - Cyberscan ONLY | Completed | quang@cyberbay.tech | Pre-event | 2025-06-30 |  | please enrol the companies to "protecthk2025" in the list below, Column B is "blank" https://docs.google.com/spreadsheets/d/1g_l0jNk4FNBBlz-bGOmLocqVXfsMjyY3OnXdsq0_EIg/edit?gid=1663119289#gid=1663119289 Only cyberscan will be run for this list and NO mission will be set up. please also check the duplicate records with different corp id, only one report for them should be fine. for example: 9e5677ff-23d1-44fa-bb26-3987efd356fe Early Light Industrial Co Ltd samuelyeung@earlylight.com.hk 23a1d204-3f0c-44ff-af2a-cc4902f13fbe Early Light Industrial Co., Ltd. pennylam@earlylight.com.hk
Bug Hunting Campaign 2025 | Upselling popup | Completed | quang@cyberbay.tech | Pre-event | 2025-07-01
Bug Hunting Campaign 2025 | Fix issue about Bug Hunting Streak page | Completed | quang@cyberbay.tech | During event | 2025-07-02
Bug Hunting Campaign 2025 | Create URL and QR code | Completed | quang@cyberbay.tech | Pre-event | 2025-07-02 |  | 1. Create URL and QR code for signup with: Promo code: protecthk2025 Referral code: PCPD2025 2. Create URL and QR code for signup with: Promo code: protecthk2025 Referral code: IGSL2025
Bug Hunting Campaign 2025 | Create URL and QR code | In progress - Dev | quang@cyberbay.tech | Pre-event | 2025-07-07 |  | 1. Create URL and QR code for signup with: Promo code: protecthk2025 Referral code: Sangfor2025 2. Create URL and QR code for signup with: Promo code: protecthk2025 Referral code: Edvance2025
Bug Hunting Campaign 2025 | Create URL and QR code | In progress - Dev | quang@cyberbay.tech | Pre-event | 2025-07-07 |  | 1. Create URL and QR code for signup with: Promo code: protecthk2025 Referral code: ricoh2025 2. Create URL and QR code for signup with: Promo code: protecthk2025 Referral code: bkpanda2025
Bug Hunting Campaign 2025 | Summarize Cyberscan reports | Completed | shaharyar Asgher | Pre-event | 2025-07-23
Bug Hunting Campaign 2025 | Send emails to Batch 1 participants | Completed | shaharyar Asgher | Pre-event | 2025-07-18
Bug Hunting Campaign 2025 | Create email templates for 180 old participants | Completed | shaharyar Asgher | Pre-event | 2025-07-16
Bug Hunting Campaign 2025 | Send summarized version of Cyberscan reports to 180 old participants | Completed | quang@cyberbay.tech | Pre-event | 2025-07-23

## Product
Category | Task | Status | Owner | Stage | Due date | Risk | Notes
Product | CyberScan Review for Premium Clients | Completed | thuy.phanthithanh@cyberbay.tech | Others | 2025-06-27 |  | Sam reviews
Product | PMTaro Desktop App | Completed | dillon.bong@cyberbay.tech | Others | 2025-07-14 |  | Dillon will be working on another felix task first, it's on hold for now, updated the new due date to 7th July. Report passed to PMTaro team, Heidi to prepare the report.
Product | Wechat MiniApps POC | Completed | dillon.bong@cyberbay.tech | Others | 2025-07-04 |  | Customer's MiniApps are not working, felix to send customer a follow up message.
Product | Bug Hunting on Bug Bounty Campaign | Inprogress | Dillon Bong | Others | 2025-08-01
Product | Bug Hunting on Bug Bounty Campaign | Not started | Sam L | Others | 2025-01-08
Product | Phishing Report for RD | Completed | Sam L | Others | 2025-07-11 |  | https://docs.google.com/document/d/1uMeikmOw7oVf9uDxoEx1yBB7jwPyqEGLFZOE4N5RpCk/edit?tab=t.0 Delivered on 02/07/2025
Product | AI Policy and Procedure Examiner | Completed | Sam L | Others
Product | AI Voice Phishing Prototype & Demo | Temporary Hold | Sam L | Others | 2025-07-31 |  | I shared an initial demo with Galina on 30/06/2025, got her feedback, and am currently working on an updated version.
Product | Video Generation for Knowledge base | Completed | shaharyar Asgher | Others | 2025-08-06
Product | Documenting and archiving the CyberWatch project and its source code | Completed | Sam L | Others | 2025-08-04 |  | Documenting and archiving the CyberWatch project, including its source code, legacy versions, databases, and associated tickets, to facilitate streamlined maintenance.
Product | Review Cyberscan Report for the 1st batch of participants | Completed | Sam L | Others |  |  | https://drive.google.com/drive/folders/1GqC8cHyw6BZepLb4VgSn2iZGNDuahv-S?usp=drive_link
Product | Nano Insure Pentest | Completed | dillon.bong@cyberbay.tech | Others | 2025-07-23
Product | Cybersecurity Challenges Report fot HKT | Completed | Sam L | Others | 2025-07-10
Others | AB Forensic and Threat Hunt | Completed | Sam L | Others | 2025-07-21 |  | Following up with AB regarding the recently identified issue...
Others | Ha Go Pentest | Reviewing | dillon.bong@cyberbay.tech | Others | 2025-07-31

## Design
Column 1 | Column 2 | Status | Owner | Stage | Due Date | Risk | Notes
Design | Corp - Account Settings | Completed | Zara A. | Others | 2025-06-27 |  | Corporate Portal - Account Settings (includes Profile Settings, Assets, Password & Security, and BugHunting Campaign)
Design | Design System Token Update | Ongoing | Zara A. | Others |  |  | Updating Figma variables and design system tokens
Design | Corp - My Profile | Design Approval Needed | Zara A. | Others | 2025-07-04 |  | Corporate Portal - My Profile (including layout, UX, and the upgrade flow for Basic Plan users) Blocker: Sales copy is late. (Owner of task - Tom / Due: Thursday, 07/10/2025)
Design | Corp - Bounty Missions UX Review | Completed | Zara A. | Others | 2025-07-14 |  | Corporate Portal - Bounty Missions page gathering insights from the team and identifying UX opportunities before the full design phase begins.
Design | Align Upselling Logic - sales/dev | Completed | Zara A. | Others | 2025-07-10 |  | Led alignment across Sales, Dev, and Design due to unapproved upselling logic being shared with dev and deployed without stakeholder sign-off. Clarified root cause, extracted blockers, and prepared fixes for urgent implementation.
Design | Plan Upgrade for General Users – Ideation & High-Fidelity Design | Completed | Zara A. | Others | 2025-07-08 |  | Conducted an ideation session to walk Tom (Sales Lead) through proposed upgrade flow for general users. Designed high-fidelity screens to support upgrade entry points across the profile page and related sections. Ensured alignment between product and sales.
Design | Mission badge components | Completed | Zara A. | Others | 2025-07-16 |  | Reviewed and updated the Mission Badge component after dev team’s front-end and back-end refactoring was completed.
Design | Review Sales Copy | Completed | Zara A. | Others | 2025-07-16 |  | Review and provide feedback on the sales copy with detailed suggestions to align it with clear, UI-friendly platform content.
Design | Corp - Bounty Missions Design | Design Approval Needed | Zara A. | Others | 2025-07-23 |  | Corporate Portal - Bounty Missions (full page)
Design | Update Sponsor Logos for BugHunting Page | Completed | Zara A. | Others | 2025-07-21 |  | Update sponsor logos for BugHunting page and send to dev team.
Design | Corp - Account Settings Design Handoff | Temporary Hold | Zara A. | Others | 2025-07-21 |  | Finalize and document the Account Settings design for the corporate portal and conduct a design handoff meeting with the development team. Dev handoff meeting - ON HOLD! Dev Team request for delay.
Design | Text Button components | Completed | Zara A. | Others | 2025-07-22 |  | Update text button components to add a set of primary and secondary text buttons with icon position on the left.
Design | Create a new badge components for plans | Completed | Zara A. | Others | 2025-07-22
Design | Media Coverage Page - Public website | Completed | Zara A. | Others | 2025-08-01

## Dev
Column 1 | Column 2 | Status | Owner | Stage | Due Date | Risk | Notes
Dev | CyberWatch Update | Completed | Sam L | Others | 2025-07-11 |  | Key tasks: Update core functions/binary to the latest version Implement a time interval for fetching news Retire the old database table and implement the new DB schema Clean and verify the database Monitor application performance in production
Dev | Lambda Resource Control API | Completed | Sam L | Others |  |  | Ticket: https://www.notion.so/Setup-EC2-Controller-Lambda-21ef6cda5915807fa7c8c69cd8dd28f9
Dev | Update CyberShadow stage in CyberScan v1 | Completed | Sam L | Others | 2025-07-09 |  | Update CyberShadow Stage binary in CyberScan v1 to work with 3th Party latest API version Ticket: https://www.notion.so/Update-CyberShadow-v1-225f6cda59158056beebd8044a604585
| Metabase SSL update | Inprogress | Quang (Brett) Ngo |  | 2025-08-08
| Corporate Dashboard Implement | Not started | Hinora |  | 2025-08-14 | High | took 2 weeks to implement
| Cyberscan Stage 6 Implement | Not started | diep.pham@cyberbay.tech |  | 2025-08-08 | Medium
| Lighthouse Debug | Inprogress | Quang (Brett) Ngo |  | 2025-08-20 | High
| Event support | Inprogress | Quang (Brett) Ngo | During event | 2025-08-31 | High
| Admin functions | Inprogress | Quang (Brett) Ngo |  | 2025-08-29 | Medium | Update some functions to statistic, update bounty, update user and others
| DB Search function Optimize | Inprogress | Quang (Brett) Ngo |  | 2025-08-22 | High

## Marketing & Sales
Column 1 | Column 2 | Status | Owner | Stage | Due Date | Risk | Notes
Marketing & Sales | Create more 2 blog posts and publish them on the Strapi | Completed | shaharyar.asgher@cyberbay.tech | Others | 2025-06-24
Marketing & Sales | Lead Generation (Qatar Fintech) Send out the 2nd sequence of UK Fintech. | Completed | shaharyar Asgher | Others | 2025-06-24
Marketing & Sales | Lead hunting - Top VPN Providers C-Level Profiles | Completed | shaharyar Asgher | Others | 2025-07-08
Marketing & Sales | Lead hunting - Random Profiles (Purchased Cybersecurity Products Recently) | Completed | shaharyar Asgher | Others | 2025-07-08
Marketing & Sales | Blog Writing (5 new blogs) | Completed | shaharyar Asgher | Others | 2025-07-04
Marketing & Sales | Lead Generation - Software Dev Agencies (Europe) | Completed | shaharyar.asgher@cyberbay.tech | Others | 2025-07-01 |  | Handed over to Tom
Marketing & Sales | Lead Generation - Energy Companies (Europe) | Completed | shaharyar Asgher | Others | 2025-07-02 |  | Handed over the list to Tom
Marketing & Sales | Refine 'Additional Offers': Option 1 (Quarterly BugBounty) and Option 2 (1-off Pentest) | Reviewing | Tom Austin | Others | 2025-07-18 |  | Completed, pending review from Galina Kho. Please see here. Please note, I've added a price for the pentest as it was missing, i've built out the offers and added some benefits too as bullet points. These are all problem-centric for our buyers/prospects and should resonate on an operational level.
Marketing & Sales | Create whitepaper for Cyberbay and the Jorge Ochillies Maturity Model and Industrial Adversarial Emulation. This doc outllines the 2 aforementioned modern cyber frameworks and then introduces Cyberbay a the key to achiving a high JCMM score and ultimately proactive continuous protection. This fits with EU energy and OT sectors. | Reviewing | Tom Austin | Others | 2025-07-18 |  | Please review the whitepaper for the JCMM and IAE, here
Marketing & Sales | Create outreach 'welcome' email for the cyberrevolution cohort | Reviewing | Tom Austin | Others | 2025-07-14 |  | heidi@cyberbay.tech Please review the email, I've canabalised the one we used previously to preserve the tone. See here
Marketing & Sales | Sales Enablement Tool Building: Jorge Ochillies Maturity Model assessment tool | Reviewing | Tom Austin | Others | 2025-07-25 |  | I've built an assessment tool for the JCMM for EU energy comapanies, we can post this on a blog (collecting emails for firms that download it, CCshaharyar.asgher@cyberbay.tech for blog ideas)
Marketing & Sales | Build a working doc of titles for a collab blog series with Datox.ai, a financial GRC automation tool - this will cross polinate our clients and prospects and will ultimately help Cyberbay win Fin sector clients in EU | Inprogress | Tom Austin | Others | 2025-07-14 |  | Please see here the working titles pending review from our partner Datox; here
Marketing & Sales | Build an outline for a workshop on GRC, Risk and cybersecurity | Inprogress | Tom Austin | Others | 2025-07-18 |  | See the workshop outline here, I'll be collaborating with Farrukh, CEO of Datox to build this out. Once we reach the right stage, i'll bring in the wider cyberbay team.

## 2025 Dashboard
Page | Section | ready for review | review results (accept / revert) | remarks
Stats | Enrollment Stage 2025 | Y
Stats | Reported Bugs ProtectHK2025 Chart
Stats | ProtectHK2025 Bugs Counts | Y | OK
Contact | Corporate Contacts | Y | OK | Data not aligned with the total count of 14 under Stats ¦ Enrollment stage 2025
Bugs
Cybershadow Scan | Pct of IPs with Vulnerabilities protecthk2025 | Y | Revert | Data not aligned with the total count of 14 under Stats ¦ Enrollment stage 2025; Cyberscan not completed for any company yet

## Sponsor
# | Date | Sponshor Name | Client referred | Contact | Title | Ref Code | Email | Registered Email | CorpID
https://community.cyberbay.tech/signup/corporate?promo=protecthk2025&referral=Oh360
https://community.cyberbay.tech/signup/corporate?promo=protecthk2025&referral=HKT2025

## 2025 Participants
# | Registration Date | Sign-up By | CorporateID | Name | Contact Email | Website Main | Cyberscan Phase 1+2 | Cyberscan Full Report | Confirm Domain Email Sent | Mission (confirmed) | Registered Email (for mission onboard) | Bounty Mission ID | Append User to CorporateID
1 | 2025-06-09 03:52 | SIGNUP | 266f2dd0-f1e8-4c55-b64a-79b96e0e850b | Inspirelab l | william.siu@inspirelab.hk | https://www.inspirelab.hk | inspirelab.hk - 16 | x | 2025-06-16 | https://www.inspirelab.hk | bughunting+Inspirelab.hk@cyberbay.tech | bVhlNDjoSPzIhgeLCwU4 | x
2 | 2025-06-09 05:46 | SIGNUP | c2947463-d44c-424d-bac7-c71521cc5815 | BIBO Limited | neteng@bibo.com.hk | https://www.bibo.com.hk | - bibo.com.hk - 27 - debtpro.com.hk - 1 - sipo.hk - 1 - digtech.hk - 1 - debtpro.hk - 0 - debtpro.xn--j6w193g - 0 - wsnfintech.hk - 0 - sipo.com.hk - 0 - digtech.com.hk - 0 | x | 2025-06-16 | bibo.com.hk | bughunting+bibo.com.hk@cyberbay.tech | mrzptKmH1jhnBf_ujG4J | x
3 | 2025-06-10 03:57 | SIGNUP | 5ac7556d-6131-42bb-9290-468476994fe9 | Hong Kong Federation of Handicapped Youth | po@hkfhy.org.hk | https://www.hkfhy.org.hk | - firstsensedesign.hk - 4 - hkfhy-sportsinclusion.hk - 3 - inclusiveguide.hk - 4 - flowerworkshop2002.hk - 5 - hkfhy.org.hk - 2 - momentum.org.hk - 4 | x | 2025-06-16 | hkfhy.org.hk
4 | 2025-06-10 06:28 | SIGNUP | 1d72ecae-5c20-4052-9d8d-c350657b6534 | Hankyu Hanshin Express (HK) Ltd. | alicelam@hk.hh-express.com | https://www.hk.hh-express.com | - hh-express.com - 46 - airtropolisphp.com - 9 - hhe-istone.com - 1 - hhe-ipark.com - 1 - hh-express.com.hk - 1 - hhe-global.com - 3 - hh-express.us - 3 - hhe-global.cn - 0 - canshabjs.cn - 1 - hankyu-kor.com - 0 | x | 2025-06-16 | www.hh-express.com.hk www.hhe-istone.com www.hhe-ipark.com | bughunting+hk.hh-express.com@cyberbay.tech | -ouXUt_g_hogLa-c4LAN | x
5 |  | Email |  | Boom Securities (HK) Ltd. | francis@boomhq.com | https://www.boom.com | boom.com | - done for boomhq.com - scanning for boom.com | 2025-06-19 | https://www.boom.com | bughunting+boom@cyberbay.tech | f3WcTwXI9BAOFED1jxxx | account found in CBB: francis.pintos@boomhq.com
6 | 2025-06-11T03:58:09.732Z | SIGNUP | e6aa228f-9e74-4d68-94d5-5e0892289059 | ECT Eichi Technology International Limited | francis@boomhq.com | ect.com.hk | - ect.com.hk - 2 - ieel.com.hk - 2 | x | 2025-06-19 | ect.com.hk | bughunting+ect@cyberbay.tech | pizUHn_Zp2k_rg4zv60a | x
7 | 2025-06-11T08:00:36.671Z | SIGNUP | 034d9bb5-a730-4c1e-82f3-590e175a76c8 | BEHL | jinzhongyang@behl.com.hk | behl.com.hk | - behl.com.hk - 3 - locdom04.com - 0 | x | 2025-06-19 | behl.com.hk | bughunting+behl.com.hk@cyberbay.tech | f-knZ-eaBisXDzpdtWAj | x
8 | 2025-06-16T08:27:36.289Z | SIGNUP | 01faff81-70b0-4541-921f-e4f3d63ea6ec | Otherland Limited | info@otherland.com.hk | otherland.com.hk | - otherland.com.hk - 3 | x | 2025-06-19 | otherland.com.hk | bughunting+otherland.com.hk@cyberbay.tech | CkhvehwwT61awt2UUr2s | x
9 | 2025-06-16T08:28:58.050Z | SIGNUP | 09da4d14-b106-4870-8a72-5bc30e8b2328 | Pak Yee Decoration Co Ltd | pakyee@netvigator.com |  | Please Deactivate account |  | Please Deactivate account | Please Deactivate account | Please Deactivate account | Please Deactivate account
10 | 2025-06-18T04:18:13.889Z | SIGNUP | 5b8660c9-7ea3-4c32-a199-eae8c1183631 | Link-Ages Collaborative Careforce | support@linkages.cc |  | linkages.cc - 2 | x | 2025-06-19 | linkages.cc | bughunting+linkages.cc@cyberbay.tech | AyEeRXslKaarTh79UMqc | x
11 | 18/06/2025 | 2024 Event | cc0c0b86-e92e-4774-bca4-b16dd6053d65 | Seito Systems Limited | chiuwing@seitopos.com |  | seito.my - 8 | x | 2025-06-19 | seito.my | bughunting+seito.my@cyberbay.tech | p3z37qGKx7Dl74_yyGQZ
12 | 18/06/2025 | 2024 Event | fd9b11b8-0ed7-41cd-ba5f-35296e76669e | Vitasoy International Holdings Ltd | Henry.Pok@vitasoy.com |  | Domains with subdomains: - vitavitasoy.com - 16 - vitasoy.com - 14 - vitasoy.hk - 5 - distilledwater.com.hk - 4 - vlt.com.hk - 3 - vitaland.com.hk - 2 - vitasoy.com.cn - 2 - calci-plus.com.hk - 1 - distilledwater.info - 1 - goryinhai.com - 1 - goryinhai.com.hk - 1 - hkgourmet.com.hk - 1 - smartvending.hk - 1 - supericy.com.hk - 1 - unicurd.com - 1 - vitajuice.com.hk - 1 - vitalemontea.com - 1 - vitasoy.ca - 1 - vitasoy.com.hk - 1 - vitasoyfruityjourney.com.hk - 1 | x | 2025-06-19 | vitasoy.com | bughunting+vitasoy.com@cyberbay.tech | Y0nFXsaerW0BhC0-2vXu | x
13 | 18/06/2025 | 2024 Event | 65ef844e-c5a9-4afe-a193-55c610bd0cf9 | 福建中學 | fms-skw@fms.edu.hk |  | - fms.edu.hk - 19 - ktslc.org.hk - 1 | x | 2025-06-19 | fms.edu.hk | bughunting+fms.edu.hk@cyberbay.tech | Re-onboard please | x
14 | 19/6/2025 | 2024 Event | fce38b83-111a-4cae-9b90-2de31ab4a8da | Swire Coca-Cola Ltd | silviaihensekhien@hk.swirecocacola.com |  | Domains with subdomains: - swirecocacola.com - 88 Domains with no subdomains (0): - cocacolaswire.com.hk - 0 - cocacolaswire.hk - 0 - cocacolaswire.tw - 0 - cocacolaswire.us - 0 - swirecc.com.hk - 0 - swirecc.hk - 0 - swirecc.tw - 0 - swirecocacola.com.hk - 0 - swirecocacola.hk - 0 - swirecocacola.us - 0 Total domains: 11 Domains with subdomains: 1 Domains without subdomains: 10 Total subdomains found: 88 | x | 2025-06-19 | swirecocacola.com | bughunting+swirecocacola.com@cyberbay.tech | XFrzuG81WdJkcWahrgnI | x
15 | 2025-06-19T02:14:52.015Z | SIGNUP | 762e48d6-a27d-4354-9e74-30fbd43ca2a9 | Madison Pacific Trust Limited | wwlee@madisonpac.com |  | madisonpac.com - 4 | x
16 | 2025-06-19T02:54:27.883Z | SIGNUP | bbf19f51-985d-4377-add4-cd35301aabcb | Union Hospital | glorialee@union.org |  | Domains with subdomains: - union.org - 21 - dhi-hk.com - 1 - dhiunion.com - 1 - hkphoto.org.hk - 1 - ihealth.org.hk - 1 - minimally-invasive-centrehk.com - 1 - my-uh.com - 1 - my-uh.info - 1 - my-uh.net - 1 - unionemc.org - 1 - unionhospital-son.com - 1 - unionpac.org - 1 - unionwomancare.org - 1 Domains with no subdomains (0): - care4u.info - 0 - dhiglobal.cn - 0 - dhi-hk.cn - 0 - dhiunion.cn - 0 - unionhospital.cn - 0 - unionhospital.org.cn - 0 - union-internalmedicine.org - 0 Total domains: 20 Domains with subdomains: 13 Domains without subdomains: 7 Total subdomains found: 33 | x | 2025-06-25 | ON Hold | On Hold | On Hold | On Hold
17 | 2025-06-19T03:35:00.590Z | SIGNUP | e8a5281b-661b-4cba-bcce-6a0c97a2d6ef | PT. Bank Mandiri (Persero) Tbk | amy.fu@bankmandirihk.com |  | bankmandirihk.com - 3 | x | 2025-06-25 | ON Hold | ON Hold | On Hold | On Hold
18 | 2025-06-19T05:11:53.398Z | SIGNUP | bebd8bc8-fc98-43cf-bae2-18a4da90a286 | City Security Company Limited | raymond.lai@cityservicesgroup.com |  | cityservicesgroup.com - 5 | x | 2025-06-25 | cityservicesgroup.com | bughunting+cityservicesgroup.com@cyberbay.tech | 3TTewS4N97hmxDp_lsgd
19 | 2025-06-19T17:35:09.713Z | SIGNUP | 961053ad-861a-419f-a6bb-4a124fd76789 | Nanyang Commercial Bank, Limited | kelvinwong@ncb.com.hk |  | Domains with subdomains: - bochk.com - 227 - ftcwifi.com - 154 - livibank.com - 58 - ncbchina.cn - 40 - ncb.com.hk - 38 - chiyubank.com - 30 - bocgroup.com - 23 - bochk-group.com - 16 - bankofchina.com.kh - 11 - boccc.com.hk - 11 - boci.com.hk - 7 - bankofchina.com.ph - 5 - bankofchina.com.vn - 5 - hkcba.com.hk - 5 - posangonline.com - 5 - posanghk.com - 4 - bankofchina.com.bn - 1 - bochkam.com - 1 - bochkholdings.com - 1 - boclifeonline.com - 1 - livibank.com.hk - 1 - livibank.hk - 1 - posangfutures.com - 1 Domains with no subdomains (0): - bankofchina.com.hk - 0 - bankofchina.hk - 0 - boc-ap.com - 0 - boc.com.hk - 0 - bocgate.com - 0 - bocgateway.com - 0 - bochk.bank - 0 - bochk.com.cn - 0 - bochk.com.hk - 0 - bocoverseas.com - 0 - bocpayment.com - 0 - ipohk.com - 0 - livibank.cn - 0 - livibank.com.cn - 0 - livibank.net - 0 - livibanks.com - 0 - nanyang-bank.com - 0 - ncb.hk - 0 - posangfuture.com - 0 - simonchansm.hk - 0 - sinobankers.com - 0 | x | 2025-06-25 | ncb.com.hk | bughunting+ncb.com.hk@cyberbay.tech | j8eQ0Xlqpnd1cMlk0-2w | x
20 | 2025-06-20T08:54:10.561Z | SIGNUP | dddc4e99-af25-42d7-bd46-c15ee643ebeb | Carrefour Global Sourcing Asia Ltd. | tommy_siu@carrefour.com |  | Root Domain Number of Subdomains carrefour.com 1182 carrefour.fr 936 carrefour.com.br 501 promocash.com 323 carrefour-banque.fr 214 carrefour.com.tw 157 centrecommercialcarrefour.fr 129 mktmaxxi.com.br 112 carrefoursolucoes.com.br 97 mktnacional.com.br 97 mafcarrefour.com 91 cybercook.com.br 79 carrefouruae.com 56 bigti.com.br 45 cartaoatacadao.com.br 41 samsclub.com.br 39 carrefourmarket.fr 32 carrefourksa.com 26 pass.fr 26 big.com.br 21 ooshop.com 21 carrefourlebanon.com 21 boostore.com 21 maxxiatacado.com.br 21 carrefourqatar.com 18 carrefour.com.cn 18 carrefouregypt.com 17 cartaosamsclub.com.br 17 carrefourjordan.com 16 assurances-carrefour.com 16 carrefourocio.com 16 echaleunamanoalmedioambiente.com 15 carrefour.net.br 15 carrefourlocation.fr 14 nolim.fr 12 nestor-elportaldelcomerciante.com 12 carrefouralgerie.com 12 carrefour.com.tr 12 centroscomercialescarmila.com 12 carrefourbanca.it 11 carrefourbahrain.com 11 carrefour.com.co 11 tiendasmetro.co 10 carrefourkuwait.com 10 grupocarrefour.com.br 10 carrefourshop.com 10 | x
21 | 2025-06-21T14:52:44.691Z | SIGNUP | cae99e73-d456-4c21-8996-c6f00e904489 | Post Easy King Limited | mabel@posteasyking.com.hk |  | posteasyking.com.hk - 2 | x | 2025-06-25 | posteasyking.com.hk | bughunting+posteasyking.com.hk@cyberbay.tech | aBAD7cm76s8ECO8JXdNl
22 | 2025-06-24 | Email - Please add back to the protecthk2025 list | 2ef8bffe-9ddb-48c0-a224-fbe4f132d63d | Bank of China Group Insurance Co. Ltd | damon_hplin@bocgroup.com |  | No need, exisitng client | x | 2025-06-24 | www.bocgins.com | bughunting+bocgins.com@cyberbay.tech | mIUI0D1neE2lG5D6Hi_s
23 | 2025-06-25T04:36:58.441Z | SIGNUP |  | Nina Hotel Group | vincentso@ninahotelgroup.com |  | "- lodgewoodhotels.com - 0 - lodgewood-hotels.com - 0 - ninaboutique.com.hk - 0 - ninapatisserie.com.hk - 0 - lhotelcausewaybayhv.com - 4 - ninahotelgroup.com - 23 - lhotelgroup.com - 20" | x
24 |  | Email - Please add back to the protecthk2025 list | e36e3978-2389-411e-ba74-7321f05edcd6 | Hospital Authority | wongwwl@ha.org.hk |  | No need, exisitng client | x |  | ha.org.hk | bughunting+ha.org.hk@cyberbay.tech | ou5uxFRJVRFdHXhqA7gV
|  | 2024 Event | e535151e-ab91-4443-bfde-a693a5f189b8 | Nan Fung Enterprises (HK) Limited | itsec@nanfung.com |  | No need, exisitng client | x |  | nanfung.com | bughunting+nanfung.com@cyberbay.tech | hxV_Hx-qFJvoqVDit7MV
|  | 2024 Event | d5b5ea03-4280-476d-97d3-fdd1954d4ecf | SNAILDY EDUCATION LIMITED | patrick.lau@snaildy.com |  | No need, exisitng client | x |  | snaildy.com | bughunting+snaildy.com@cyberbay.tech | qEkFiUFJDiHLzM6DTc5U
|  | 2024 Event | ecc55cbc-afee-43d6-8a3f-d1fd9eec82f6 | The Hong Kong Society for the Aged | terry.lau@sage.org.hk |  | No need, exisitng client | x |  | sage.org.hk | bughunting+sage.org.hk@cyberbay.tech | J18ayKjLjH5mrFBGnz-M
|  | 2024 Event | a98743e9-1cb7-4e4b-8503-c00eb081d740 | VANKE HOLDINGS (HONG KONG) COMPANY LIMITED | ivancheng@vanke.com |  | No need, exisitng client | x |  | vanke.com | bughunting+vanke.com@cyberbay.tech | jXzov4WSssm7WzPvE5Bo
|  | 2024 Event | 2af672ba-d7b5-48c5-bd3e-91b32b126958 | Rakuten Securities Hong Kong Limited | tony.tsang@sec.rakuten.com.hk |  | No need, exisitng client | x |  | sec.rakuten.com.hk | bughunting+sec.rakuten.com.hk@cyberbay.tech | G5DGZ3uxf9dw59ya9NwE
|  | 2024 Event | 336b2ad5-e0b3-4226-9694-cd9bcc0eb72a | AKA | ivanlo.ch@aka.org.hk |  | No need, exisitng client | x |  | aka.org.hk | bughunting+aka.org.hk@cyberbay.tech | MvYmqjdmgsFj2YH5i7t7
|  | 2024 Event | 0d95839f-f981-4e77-85b3-fe54f0ce3d53 | Wah Sum Electrical Engineering Supplies Ltd | patrick@wahsum.com.hk |  | No need, exisitng client | x |  | wahsum.com.hk | bughunting+wahsum.com.hk@cyberbay.tech | 1dyB9_X6-PTnmrLDeH_w
|  | 2024 Event | c38570a1-efae-4ac2-a297-e27f52f02b2a | MyTV Super Limited | kristy.lau@tvb.com |  | No need, exisitng client | x |  | http://mytvsuper.com/ | bughunting+mytvsuper.com@cyberbay.tech | KQX5dcrq8pq20ZCUmwpZ
|  | 2024 Event | 11caa35a-3c05-406b-9b53-da235d38d66a | The Hong Kong School of Motoring | patrickcheng@hksm.com.hk |  | No need, exisitng client | x |  | hksm.com.hk a1driving.com.hk leinam.com.hk nktds.com.hk meg.com.hk | bughunting+hksm.com.hk@cyberbay.tech | nuFewse1XN96Fr2fiHc4
|  | 2024 Event | 8124c816-cb28-45fe-96ce-a4ba23b1fc22 | Our Hong Kong Foundation | lawrence.li@ourhkfoundation.org.hk |  | No need, exisitng client | x |  | ourhkfoundation.org.hk | bughunting+ourhkfoundation.org.hk@cyberbay.tech | mGsM1zUktFI3HPflBhvH
25 | 2025-06-25T04:36:58.441Z | SIGNUP | f1f1e541-bb77-4120-ac78-db5b344714f3 | Nina Hotel Group | vincentso@ninahotelgroup.com | https://www.inahotelgroup.com | - lodgewoodhotels.com - 0 - lodgewood-hotels.com - 0 - ninaboutique.com.hk - 0 - ninapatisserie.com.hk - 0 - lhotelcausewaybayhv.com - 4 - ninahotelgroup.com - 23 - lhotelgroup.com - 20 | x
26 | 2025-06-25T10:22:02.603Z | SIGNUP | f047b79d-2907-41fd-add0-00548876a1b1 | Hong Kong Chronicles Institute | admin@hkchronicles.org.hk | https://www.hkchronicles.org.hk | - hkchronicles.org.hk - 5 | x | 2025-06-27 | hkchronicles.org.hk | bughunting+hkchronicles.org.hk@cyberbay.tech | SGa8nzo3V__9UgQCuEgG
27 | 2025-06-26T03:26:05.439Z | SIGNUP | 893fb9b8-d61e-4dda-aef4-80b18dbe6626 | The Academy of Chinese Studies | admin@acsohk.org.hk | https://chiculture.org.hk | - acsohk.org.hk - 1 | x | 2025-06-27 | chiculture.org.hk | ha.org | cHTosGBmbpEDU6IkuKLo
28 | 2025-06-26T06:57:42.875Z | SIGNUP | 14ff7caa-8297-4eb9-b223-854bbf44af5c | KLN Logistics (HK) Ltd | joejoe.wing@kln.com | https://www.kln.com | - efthardwood.info - 0 - caramall.com.hk - 0 - woodeft.com - 0 - environmentallyfarmedtimber.org - 0 - kln.com - 34 - woodeft.org - 0 - woodeft.net - 0 - environmentallyfarmedtimber.info - 0 - karrion.com.hk - 0 - efthardwood.org - 0 - qfma.net - 0 - kln.us - 1 - environmentallyfarmedtimber.net - 0 - woodeft.info - 0 - environmentallyfarmedtimber.com - 0 - efthardwood.net - 0 - efthardwood.com - 0 | x | 2025-06-27 | kln.com | bughunting+kln.com@cyberbay.tech | Qep8QU3V1skcIIpN1TT8
29 | 2025-06-27T00:29:20.235Z | SIGNUP | 81e64a0f-8771-4b1f-80e2-d8f4f41438b0 | Musical Electronics Limited | it@musical.com.hk | https://www.musical.com.hk | - musical.com.hk - 2 - soukihk.com - 0 | x | 2025-06-30 | musical.com.hk | bughunting+musical.com.hk@cyberbay.tech | E6EL1-e2IomY90r4C2BZ
30 | 2025-06-27T02:59:13.516Z | SIGNUP | abf14f92-162b-41d2-9fda-5354e40b43dc | Yip's Chemical (Holding) Ltd. | alvin.chow@yipschemical.com | https://www.yipschemical.com | - bauhiniahk.com.hk -1 - camelpaint.com.cn - 1 - yipscef.com.hk - 1 - yipsz16.site - 0 - hc.com.hk - 1 - pacoil.com - 1 - yipschemical.com - 13 - dc-polymer.com - 1 - yipsoa.com - 7 - camel.com.hk - 3 - yipsab.info - 0 - yipscorp.com - 4 - handsomechemical.com - 2 - yipshc.com - 1 - yipslube.com - 0 - xn--tfru0muusc1az6b.com - 0 - yipsink.com - 2 - bauhiniapaints.com - 0 - bauhiniapaints.info - 0 | x | 2025-06-30 | yipschemical.com | bughunting+yipschemical.com@cyberbay.tech | w-o8I3W7mpYSo8cRPm96
32 | 2025-06-27T04:24:27.986Z | SIGNUP | d0d9696b-8a2b-49be-9354-daf24ed3a45a | HKEAA | infosec-reg@hkeaa.edu.hk | https://www.hkeaa.edu.hk | - hkbca.edu.hk - 0 - hkeaa.edu.hk - 65 - pess-hkeaa.edu.hk - 10 | x | 2025-06-30 | hkeaa.edu.hk | bughunting+hkeaa.edu.hk@cyberbay.tech | K3Pr7Am5wtYKsX8X6ES1
|  | SIGNUP | b6e835a1-ee01-45e2-8ac5-bc4e737a3bde | 3YwTjB9IECwSATFWNEsW | ann@tungyick.com.hk |  |  | x |  | tungyick.com.hk | bughunting+tungyick.com.hk@cyberbay.tech | 3YwTjB9IECwSATFWNEsW
|  | SIGNUP | b9c80ae2-9500-4776-b270-fbb782b52567 | The Hong Kong University of Science and Technology | ccbill@ust.hk | https://hkust.edu.hk/ ust.hk |  | x | 2025-07-04 | hkust.edu.hk ust.hk | bughunting+hkust.edu.hk@cyberbay.tech | 8YPd7TJ0DdnuT_sW7HfU
|  |  | 0d9a5302-6aa7-4656-9676-9b2dd1e104a6 | Fubon Securities HK | peter.w.cheng@fubon.com |  |  | x | 2025-07-11 | fubonsec.com.hk | bughunting+fubon.com@cyberbay.tech | KcsaTuL4XmRnQxt1fDGG

## Previous Year Pariticpants
Corp Repliies | Dev Team Follow up |  |  | Heidi Follow up
Setup Missions | CyberScan + Create support account + set up missions
No Reply till 24 June | CyberScan ONLY |  |  | One more email on 24 June, we will only send you the CyberScan report, but if you change your mind within 24 hours , please let us know and we will handle the enrollment for you
Opt Out | DO NOT set up anything
Reply email Date | Action | CorporateID |  | Name | Contact Email | Confirmation email sent | Cyberscan Phase 1+2 | Mission | Generated Cyberbay Scan PDF?
|  | c0d96274-c1c4-404b-84b2-3e27e956fae2 | x | 7-Style Development (Sugar) Limited | andrewlee@7-style.com.hk
|  | de8337d6-db11-489e-97bb-44391d8d54d2 | x | AirStar Bank | anson.tsai@airstarbank.com
|  | 7536f43c-7b0e-419e-bc89-85568c803454 | x | Airstar Bank Limited | davy.chui@airstarbank.com
|  | 06a11e81-837a-4e94-a100-3561004315fe | x | Allied Banking Corporation (HK) Ltd. | andy@abchkl.com.hk
|  | e86fabe7-08e7-42ed-bc40-c442c017dc79 | x | Alva Hotel by Royal | mingchan@alva.com.hk
|  | fc5ebeeb-8a9b-4af9-a321-983e7e283da1 | x | APC Asia Pacific Cargo (H.K.) Ltd | simon.lau@apclogistics.com
|  | 92974ab4-d928-493f-971e-701bcb2b7baa | x | Assembly of God Choi Po Gospel Church | soman@choipochurch.org
|  | e9845f9e-d0e5-4133-ab94-95f1f015f9d5 | x | B&D | kenwong@bdata.com.hk
|  | 4ff9ca3a-cc65-41d4-866e-15c5e1761b55 | DNS not found | BeeShared | info@beeshared.co
|  | 806d17d3-baed-4898-9300-9a488194ab9c | x | Berlin Finance Group | victorpun@berlin.com
|  | abc054b0-3dfb-4900-90ad-b4827cc76373 | x | Bond Connect Company Limited | louislau@chinabondconnect.com
|  | 88f7c0d2-ca42-4fa9-9b69-32e4ee44e74d | x | Caitong securities (Hong Kong) Co., ltd. | robin.lam@ctsec.com.hk
|  | 458a9494-da13-48fa-8115-518e236e2fbe | x | Chinese Estates Holdings Limited | joeyf.chan@chineseestates.com
|  | 6e0e3f1c-eeae-4112-b3f4-bbf5e8b4b7b4 | x | C-HR Company | clarence.lee@employee.com.hk
|  | 3e2c4d0e-c994-409c-a416-3f31fb4b1c1f | x | CITIC Pacific Ltd. | andyshih@citicpacific.com
|  | 09a5dcd5-a814-432e-8a00-26738a818e91 | x | Citybase Property Management Limited | vincent.cheung@citybaseltd.com
|  | 407c37a0-ce03-448c-a7fd-b43bb80eafb3 | x | CONNAUGHT CASES LTD. | jennifer@cases.com.hk
|  | fbf37536-1bd7-4340-935d-5fbdbfecedab | x | ConnectedGroup | yiuwa.ho@connectedgroup.com
|  | 682b8348-8e71-4868-b847-d66ac5113c58 | x | Cuisine Continental Group HK Limited | prestian.liu@cuisinecontinental.com
|  | 13b7ef3a-0d43-4be9-a510-bb74c4e9390f | x | Custonomy Company Limited | generaladmin@custonomy.io
|  | 2dbf6fc7-f945-424d-8faf-fb035f616e46 | x | Daikin Airconditioning (Hong Kong) Ltd. | it@daikin.com.hk
|  | 7d4a2f26-034e-49dc-829e-52af55909c28 | x | Datality Lab Limited | roland.leung@datalitylab.com
|  | ec189d1b-a781-4aa0-b5c5-9b81bcc64464 | x | Defypay Limited | perry@defypay.io
|  | 72616f28-5602-4e8b-a7bc-3676aabe8173 | x | Dr.Kong Footcare Limited | it@dr-kong.com.hk
|  | 9e5677ff-23d1-44fa-bb26-3987efd356fe | x | Early Light Industrial Co Ltd | samuelyeung@earlylight.com.hk | Duplicate
|  | 23a1d204-3f0c-44ff-af2a-cc4902f13fbe | x | Early Light Industrial Co., Ltd. | pennylam@earlylight.com.hk | Duplicate
|  | 5bee7b67-24f5-4b0b-a88d-b8e2ab7f6f51 | x | Egg technologies ltd | alex@eggtechs.com
|  | 3ebcbe6c-2f7e-4fa8-8eba-6b6dd92a84d4 | x | Ergatian Limited | jadylee@ergatian.com
|  | 29f4b954-f6b7-4438-90f8-4f323bf1830d | x | ESG Hong Kong Limited | marketing.hk@esghl.com
|  | d9d716a0-95ca-4d2c-89b9-9fa9ead3ae82 | x | Esquel Enterprises Limited | wongiv@esquel.com
|  | b8438278-728c-4e68-b812-13347b198b0b | x | EventX | angus@eventx.io
|  | fe6cbee8-37ed-48eb-9fb9-7363028b7bca | x | Federation of Hong Kong Industries | eric.wong@fhki.org.hk
|  | 1f5b1ff4-5b10-4deb-9022-24771b59e6ca | x | FICO International Ltd | debbie-wines@sunwahgroup.com
|  | fb6c71f2-7abc-447e-a85a-89b6421f610f | x | Global Technology Integrator Ltd. | michelle.mak@gti.com.hk
|  | 73e0ed8b-79db-4281-a6c8-d784da850787 | x | Go4fiber | garykl-wong@go4fiber.com
|  | a92ad24e-a309-4381-af31-8088274ab126 | x | Guotai Junan International Holdings Limited | jacky.chan@gtjas.com.hk
|  | 940cd31a-7780-460f-b216-f4fe8dd73917 | x | Hip Shing Hong (Holdings) Company Limited | andychoi@hshd.com.hk
|  | 3d44d617-830f-4173-b946-6a0bdfd6d709 | x | HK Convention and Exhibition Centre (Management) Limited | frankong@hkcec.com
|  | 5eecf3b7-eaed-4eea-bf01-66e604d281bf | x | HKFYG | mavum.cheung@hkfyg.org.hk
|  | 5417ecc5-bebc-4398-9b26-808decae8896 | x | HKU SPACE | cf.yeung@hkuspace.hku.hk
|  | 2ee2c6a5-df18-4586-a72f-a52b0a990c69 | x | HMC | charles_lee@hmc.honda.com.cn
|  | 52c57788-6b72-482e-8c4f-f6d7415d81a1 | x | HMS | products5@hkmedsup.com.hk
|  | 9de2e698-d94a-4e5a-a419-898135665012 | x | Hong Kong Baptist Hospital | paulmanpmlau@hkbh.org.hk
|  | 176c33bb-abb7-4704-9adf-08a61b3f4c9d | x | Hong Kong General Chamber of Commerce | stong@chamber.org.hk
|  | 3662c328-7f6e-4034-aabd-8f69cd31acbe | x | Hong Kong Green Building Council | it@hkgbc.org.hk
|  | bfad78b1-9148-4720-95ce-d1b1e1df42df | x | Hong Kong Institute of Clinical Psychologists | icp@icphk.org.hk
|  | 050b3015-7d59-4eb6-a0cc-08777fba71fc | x | Hong Kong Red Cross | anson.lok@redcross.org.hk
|  | 7a4d32b9-54fa-42e2-98af-ceb13a7a1bb6 | x | Hong Leong Bank Berhad | hugh.lim@hlb.com.hk
|  | 9313880d-2ac9-4ebf-b8cc-dcacd5798480 | x | Hotel ICON | kenneth.cheung@hotel-icon.com
|  | 208b7ef9-d592-4c01-bc81-6444f337cd8d | canceled | Inter-Pacific Holdings Ltd | sunning@netvigator.com
|  | f5b1d35c-147d-4d1c-9328-647128d3d7a7 | x | IPP INTERNATIONAL WEALTH MANAGEMENT LIMITED | gordonshum@ippfa.com.hk
|  | 290dad1f-221e-49b3-a460-bbfb6186c087 | x | JETCO | itsm@jetco.com.hk
|  | 4a69f606-3406-4b33-9cc0-f6c14df26b1a | x | JS Global Lifestyle Company Limited | stanley.chan@jsgl.com
|  | df2466d1-fd2f-49a4-809d-a676167fe2f7 | x | Just A Moment Wellness | info@jamwellness.io
|  | 098ec99e-5617-4c6b-a184-791dd5dc2fa5 | x | Kadoorie Farm and Botanic Garden | linden.ying@kfbg.org
|  | 2fbcab54-ab30-4cd0-8824-8c31cf1f744f | x | Kai Shing | ksit@kaishing.com.hk
|  | e4ffb2bf-fa14-48cd-8588-cd163561aa0b | x | KHI Management Ltd. | yw@khiholdings.com
|  | e38b952d-c6d9-429d-8041-e39b8e29489d | x | Langham Hospitality Group | Michael.kwok@langhamhotels.com
|  | 111a28bb-7ac9-407c-a289-af6d1d2d52fd | x | LAWSGROUP | judy.chan@lawsgroup.com
|  | 00cc29b2-dc48-4cd0-afd1-5895a6beb55f | x | LBS Corporation Limited | raymondtam@lbsgroup.com.hk
26/6/2025 | Setup Mission - HKSM | c15ebb4a-5fad-4e46-9c36-dedf03537b62 | x | Leinam School of Motoring Limited | admin@leinam.com.hk
|  | 88d38c3e-1db6-4972-b870-cb3bfd309116 | x | Linnovate Partners Limited | samson.law@linnovatepartners.com
|  | c9ec5412-508f-466f-bc66-fed2e65ac02d | x | LOST | rick@losthk.com
|  | 5f57708f-7e6f-43dd-b49a-956e8fc24bdf | x | Lucky Engineering Co Ltd | kentleung@luckyeng.com.hk
|  | aeb85571-9e6d-4ef7-a700-8fbab4015970 | x | Makita Power Tools (HK) Ltd | paul.wong@makita.com.hk
|  | 862787f4-b22b-4da8-872d-928f82b50e15 | x | Management Company of Olympic House Limited | ericchan@hkolympic.org
|  | 39cde1b0-77ed-4d59-adad-99781e4083a4 | x | M & R FORWARDING (H K) LTD | jimmy.ouyang@hk.mrspedag.com | Only Scan cargoemotion.com
|  | dd2a3c05-d4e8-45da-9dcd-e4872d5cc34d | canceled | NONE | allblue_zero@yahoo.com.hk
|  | 87d9fb03-b320-4bfd-9d46-0b4b11ea0349 | x | Nouvelle | samuel.chan@nouvellebiotech.com
|  | 600c7303-5099-49a3-b85e-ea3992c6864a | x | One-Eight-One Hotel & Serviced Residences | kyleheung@one-eight-one.com
|  | fa8e1f86-e1ef-40a0-8c93-46b81c890a19 | x | P&T Architects Limited | simonlam@p-t-group.com
|  | fa8e1f86-e1ef-40a0-8c93-46b81c890a19 | x | P&T Architects Limited | pthkit@p-t-group.com
|  | 3acbffd5-2786-4033-8d00-b5439a42612d | x | Pure International Limited | infra-mgmt@pure-international.com
|  | 220622c8-fa72-4092-abdd-6d4e61d7a99e | x | Reimagine Cyberbay Ltd | felix.kan@cyberbay.tech
|  | 0184e402-41c6-456f-b9eb-4dcf06c78e35 | x | Royal Park Hotel | ryancheung@royalpark.com.hk
|  | c08744cb-270d-400d-b6f9-5fa1421500cb | x | S.A.S. Dragon Holdings Ltd | simonwong@sasdragon.com.hk
|  | 2163d44b-a5d3-4e7e-947a-5916cdf0390d | x | SEATRANS SOLUTION LTD | herman@seatranshk.com
18/06/2025 | Setup Missions | cc0c0b86-e92e-4774-bca4-b16dd6053d65 | x | Seito Systems Limited | chiuwing@seitopos.com | Y
|  | 4c99e1e6-2412-4c83-bd5b-6d03fa0bdec6 | x | Sky Business Centre | evonchung@skybizcentre.com
|  | f1ad1759-98b0-4fd9-882c-445ea6ee491d | x | South Asia Knitting Fty Ltd | samng@southasiagroup.com
|  | 0bbca253-e6d9-4918-8a8d-3a7c4af3ccaf | x | South Asia Textiles (Holding) Ltd. | samng@southasiagroup.com
19/06/2025 | Setup Missions | fce38b83-111a-4cae-9b90-2de31ab4a8da | x | Swire Coca-Cola Ltd | silviaihensekhien@hk.swirecocacola.com | Y
|  | 3eef6912-a6c2-4507-a399-d5b30e1fcfbb | x | Tam Jai International | kavier.ku@tamjai-intl.com
|  | 931cafda-d034-4d3d-9707-1964debd0039 | x | tay | tay@taypoc.com
|  | b65887c9-5bfa-4bb1-a2d3-0d4789d2b7f9 | x | The Harilela HK | nick.tsang@thehari.com
|  | 0442df49-5928-467e-bc7e-3ee1f6f4db02 | x | The Helena May | gm@helenamay.com
|  | 5189f981-e82d-4392-bc3e-697f9bf66eea | x | The Hong Kong Academy of School Managers Limited | hkasm2013@hkasm.org.hk
|  | 11caa35a-3c05-406b-9b53-da235d38d66a | x | The Hong Kong School of Motoring | patrickcheng@hksm.com.hk
|  | 5c9dc11c-2133-4733-abfd-bd6263ec3a7d | x | The Royal Garden | dantse@rghk.com.hk
|  | 15f7bea5-e882-4ced-b740-293280ccc98e | x | The YMCA of Hong Kong | tonyfung@ymcahk.org.hk
|  | e82139dd-67bb-4bc7-8bb4-ee8190f547c6 | x | TradeLink Technologies Limited | lewis.ling@tradelinkone.com
|  | a3245078-62dd-4869-8234-b505fc241c54 | x | Tung Wah Group of Hospitals | eveline.kwok@tungwah.org.hk
|  | be6ad4a1-dd54-445e-9d55-64e8b75a256c | x | Tung Wah Group of Hospitals Lee Ching Dea Memorial College | fty@lcdmc.edu.hk
|  | b0e009cd-0e72-495e-9846-8505c6ea3eaf | x | U F M Computer Service Company Limited | tyyau@ufm.com.hk
| Signed up | 22befc11-7913-4c3d-bb4b-b82f3247c1ff | x | Union Hospital | evachanyl@union.org
|  | 4c063881-33cd-4c58-bc29-d07a4d98b38f | x | Unique Timepieces Watches Holdings Limited | elvisechen@utpieces.com
|  | 9ce6affe-c6d8-47eb-aeaf-69d2d95f89d5 | x | Village Telephone Limited | shelleyng@villagebroadband.hk
18/06/2025 | Setup Missions | fd9b11b8-0ed7-41cd-ba5f-35296e76669e | x | Vitasoy International Holdings Ltd | Henry.Pok@vitasoy.com | Y
|  | e5b6e08a-cb89-474f-a860-0ff97b220834 | x | Water Oasis Group Limited | garylui@wateroasis.com.hk
|  | 01d186fc-3e1e-4dfc-8a0c-ea1b12af5efb | x | Weltronics Component Limited | terry.law@weltronics.com
|  | 81bdc538-9914-4443-ae8c-08bc1d866866 | x | wizlynx group | mike.lo@wizlynxgroup.com
|  | ea02e176-8336-45b9-b48e-ba9fa831c7e6 | x | World Vision Hong Kong | supportservices@worldvision.org.hk
|  | b4cd1f41-6a3a-48a2-b87f-022449fd3749 | x | YMCA of Hong Kong | kmkwan@ymcahk.org.hk
|  | 9fb1d066-a86f-4ba9-b1ab-b8bc6fd62579 | x | YU CHUN KEUNG MEMORIAL COLLEGE NO.2 | itavadmin@yck2.edu.hk
|  | 507b1c1d-3292-4da8-a1b7-13237e344c09 | x | 基督教香港信義會 | chuipingchak@elchk.org.hk
18/06/2025 | Setup Missions | 65ef844e-c5a9-4afe-a193-55c610bd0cf9 | x | 福建中學 | fms-skw@fms.edu.hk | Y
25/6/2025 | Setup Missions | 0d95839f-f981-4e77-85b3-fe54f0ce3d53 | x | Wah Sum Electrical Engineering Supplies Ltd | patrick@wahsum.com.hk
|  | 253596ca-a297-4aea-84f2-cc38d658de9c | x | NFC Touch Limited | stephen@nfctouch.com.hk
|  | 25b151ce-c2a7-4c06-83a7-f0a491f138e8 | x | Qooverse Interactive Limited | kyle@qooverse.com
| Setup Missions | 2ef8bffe-9ddb-48c0-a224-fbe4f132d63d | x | BANK OF CHINA GROUP INSURANCE COMPANY LIMITED | damon_hplin@bocgroup.com | Y
|  | 3848a3ef-bb69-42ba-9763-1dc5df6a4a1e | x | Competition Commission (Hong Kong) | simonleung@compcomm.hk
|  | 3ac58899-f017-4ee0-865c-77c36f270f57 | x | K.Leaders Business Consultants Limited | bchan@k-leaders.com.hk
|  | 3ebb7e6f-08ce-4d76-90b0-e553f0649d7b | x | Just Chat AI | info@justchatai.com | Scan app.justchatai.com
|  | 538dfb62-fd06-46e5-a697-3d1c7dfa69cc | x | Butler Asia (Mayfair Enterprises Ltd) | chi@butlerasia.com
|  | 5502b858-b1d5-4bc9-b563-96b81d0f980d | x | Deacons | jeremy.au@deacons.com
|  | 6328dce0-8f52-4a67-80be-5660bf729ddd | x | JME Group Ltd | info@temptattooidea.com
|  | 6e3f178e-bc03-4078-aa59-36f1a4850c46 | x | Angelflow Limited | sean@angelflow.vc
|  | 71eb40c2-5b13-43af-bb65-de185efb0552 | x | HKSI | dennischeung@hksi.org
|  | 7600cdc0-cd43-4c2b-ba16-8e79d4ccd5cf | x | ImagineX Group | alanlai@imaginex.com
|  | 7e73d1fc-772f-4aa7-be03-ef9176831da4 | x | Bank Consortium Trust Company Limited | itsec@bcthk.com
|  | 84869a9b-58df-4e95-85ad-a75541d28cba | x | THE WHARNEY GUANG DONG HOTEL HONG KONG | it@wharney.com
|  | 9108e3b5-cc91-458a-83cf-f019503e7f4c | x | Yoho Group Holdings Limited | winkieliu@yohohongkong.com
|  | 96d02c8d-ebc3-4a2a-9294-cd5f8f5b24df | x | InspiringHK Sports Foundation Limited | hollywu@inspiringhk.org
|  | 97a8046e-c4f8-4027-85f0-8a8deed7e6f8 | x | Integrated Global Solutions Limited | ben.cheung@igsl-group.com
|  | 9b0e3dec-d2b2-4767-a015-74ffbd7e5de5 | x | Hong Kong Broadband Network Limited | william.yu@hkbn.com.hk
|  | ae896d10-62ca-4d22-8e00-f537ff83989f | x | THE CHINESE GENERAL CHAMBER OF COMMERCE | larry@cgcc.org.hk
|  | aedd22d6-59c5-4c77-945e-885a44d7d7fd | x | SecurePro Technology Security System Limited | john@securepro.com.hk
25/6/2025 | Setup Missions | c38570a1-efae-4ac2-a297-e27f52f02b2a | x | MyTV Super Limited | kristy.lau@tvb.com
|  | d30d0682-f836-4507-a91f-73667ef6211f | x | The Hong Kong Award for Young People | stanleylam@ayp.org.hk
|  | dadd6717-008a-47a2-b1f4-31163f0627a9 | x | Avotech | john@avotech.com
|  | de041f6b-c987-4158-9ee3-b9ef594f439b | x | Sang Creations Limited | webmaster@learningchocolate.com
| Setup missions | e36e3978-2389-411e-ba74-7321f05edcd6 | x | Hospital Authority | wongwwl@ha.org.hk | 2025-06-22
|  | e5ac2b59-6cab-431b-9e4f-76a51dc34b52 | x | Artin Mosaic Limited | kh.hung@artinmosaic.com
|  | f0da25a5-dfaf-475b-b4d0-7bb97eb8fc34 | x | Evangel Hospital | louischoi@evanhosp.org.hk
26/6/2025 | Setup Mission - HKSM | 7c999e33-a9ea-44ba-a054-8b4fbec0bb73 | x | A1 Driving School Limited | admin@a1driving.com.hk
|  | 3cd86634-b669-4703-8510-bd249d51b4f5 | x | Kadoorie Estates Limited | dicksonlee@kadoorieestates.com.hk
|  | f0af9f48-f677-4695-9c16-26e54386f006 | x | MTR Corporation Limited | justinhmlaw@mtr.com.hk
| Setup missions | e535151e-ab91-4443-bfde-a693a5f189b8 | x | Nan Fung Enterprises (HK) Limited | itsec@nanfung.com
26/6/2025 | Setup Mission - HKSM | 3e1e775c-3149-4b5c-96dc-09163a4dc687 | x | NKT Driving School Limited | admin@nktds.com.hk
|  | c299df88-1ef4-48dd-bab9-0c16e41f36ff | x | SikSikYuen | itosubscribe@siksikyuen.org.hk
2025-06-19 | Setup missions | d5b5ea03-4280-476d-97d3-fdd1954d4ecf | x | SNAILDY EDUCATION LIMITED | patrick.lau@snaildy.com
| Setup missions | ecc55cbc-afee-43d6-8a3f-d1fd9eec82f6 | x | The Hong Kong Society for the Aged | terry.lau@sage.org.hk | Y
|  | e28dca98-01ff-4eb0-8564-4d60ca568c26 | x | Thinking Technology Limited | kh.hung@thinking.com.hk
| Setup missions | a98743e9-1cb7-4e4b-8503-c00eb081d740 | x | VANKE HOLDINGS (HONG KONG) COMPANY LIMITED | ivancheng@vanke.com
|  | 92727056-e275-47e3-8ca2-c8c2eef25e0c | x | Youth Outreach | ricky.wu@yo.org.hk
2025-06-25 | Setup missions | 2af672ba-d7b5-48c5-bd3e-91b32b126958 | x | Rakuten Securities Hong Kong Limited | tony.tsang@sec.rakuten.com.hk
| Setup Missions | 336b2ad5-e0b3-4226-9694-cd9bcc0eb72a | x | AKA | ivanlo.ch@aka.org.hk
2025-06-26 | Setup Missions | 8124c816-cb28-45fe-96ce-a4ba23b1fc22 | x | Our Hong Kong Foundation | lawrence.li@ourhkfoundation.org.hk | 2025-06-26
|  | 3186e424-4fb9-497c-a113-f6c08a1d3d21 | x | FinTech Association of HK | generalmanager@ftahk.org

## Heidi Bounties Tracking
Bounty ID | Corp Name | Reward amount manual update | Purchased report amount (HKD) | Remarks
G5DGZ3uxf9dw59ya9NwE | Rakuten Securities Hong Kong Limited | 4200 ¦ 3000 ¦ 600 | 5500 | One Report Purchased under 2024 missions | Tier 1: Default Value: 7000 ¦ 5000 ¦ 1000 , Cumulative Total>= 5000 to Tier 2
Tier 2: Default Value: 4200 ¦ 3000 ¦ 600 , Cumulative Total>= 8000 to Tier 3
Tier 3: Default Value: 2520 ¦ 800 ¦ 0